## Slide 1
PHASE 1
© 2018 Synectiks. All Rights Reserved. Proprietary and Confidential.

## Slide 2
M1 S1
M1 S2
M2 S3
M2 S4
M3 S5
M3 S6
M4 S7
M4 S8
Design Sprints
Development Sprints
Implementation
IT1 Modules
Requirements Documentation
S0
Sprints
S1
S2
S3
S4
Future Phases
Prod Environment Setup
S5
S6
S7
S8
Iteration 2
Activities
Use Case
UX Design
Review
Artifacts
Use Cases
Design Prototype
Use Case
Activities
Implement IT3 Modules
Feed Back / Changes
User Guide
Artifacts
IT3 Modules
User Guide
Implementation
Activities
Test / Change
Artifacts
ATP results
Verification
Production Movement Sprints
Proposed Project Timeline
Timeline
Activities
Implement PH1 Modules
Deployment
User Guide
Artifacts
IT1 Modules
User Guide
Implementation
Activities
Implement IT2 Modules
Deployment
User Guide
Artifacts
IT2 Modules
User Guide
Implementation
Iteration 3
Iteration 1
Implementation IT1 Modules
Acceptance
Activities
Deployment
Release
Operation
Artifacts
Production App
Deployment
© 2018 Synectiks. All Rights Reserved. Proprietary and Confidential.

## Slide 3
Methodology
When recommending an Agile execution approach, Synectiks considers the following core activities and concepts to be the most critical to the success of project execution. While we are willing to be flexible on our execution approach, we believe that eliminating these activities reduces the effectiveness of the agile approach.
Process & Approaches
Release plan / product backlog
Sprint backlog
Sprint goal
Sprint closure
Vision, ROI and project cadence
Creation of themes, epics and user stories
Prioritization of backlog items and grooming
Deployment activities
Showcase / demonstration
UAT
Backlog grooming
Retrospective
Release burn-down
Develop definition of “Done”
Sprint backlog refinement
Develop acceptance criteria
Assign story points
Develop testing approach
Create, develop and assign tasks
Daily Scrum meetings
Development
Weekly builds and reviews
Continuous integration and testing
Impediment removal
Update documentation
Release plan
Product backlog
Release burn up
Working Software
Retrospective backlog / action list
Continuous improvement plan
Defect management
Release burn-down
Sprint backlog
Definition of “Done”
Test approach
Acceptance criteria for each story
Sprint Goal
Documentation approach
Impediment tracking list
Sprint backlog prioritization
Sprint burn-down chart
Kanban / Scrum board
Defect management
Development documentation
Activities
Output
© 2018 Synectiks. All Rights Reserved. Proprietary and Confidential.

## Slide 4
Methodology
Assumptions:
2 weeks design / development sprints
Daily scrum check-in meetings
Acclaro Roles & Responsibility
  Require Product Owner role from customer to Articulate product strategy, vision and roadmap to stakeholders
  Prioritize and manage product back log.
  Synectiks representative to participate in daily scrum, sprint planning and retrospect meetings.
Synectiks Roles & Responsibility
Synectiks PM along with developers participate in daily scrum and report status
Synectiks PM mitigate any risk from software delivery perspective.
© 2018 Synectiks. All Rights Reserved. Proprietary and Confidential.

## Slide 5
Development Principle
We build custom solutions based on Cloud Native principles with micro-service-based architecture , driven by DevSecOps approach to add development velocity and site reliability. While we are willing to be flexible on our execution approach, we believe that adopting the most modern technology stacks and architecture principles are critical to the project success.
© 2018 Synectiks. All Rights Reserved. Proprietary and Confidential.
Architectures & Development

## Slide 6
Effort
Task | Role | Effort | Pricing
Product and Release Management | Project Manager | 4 Man Months | Rate 20 USD/Hr 4*160*20=12800 USD
Architecture and Planning | Architect | 1 Man Week | Rate 60 USD/Hr 40*60=2400 USD
UX Design | UX Designer | 2 Man Month | Rate 25 USD/Hr 2*160*25= 8000 USD
UI Development | UI Developer | 2 Man Month | Rate 20 USD/Hr 2*160*20= 6400 USD
Backend Development | DevOps | 4 Man Month | Rate 30 USD/Hr 4*160*30= 19200 USD
Business Analysis | Business Analyst | 4 Man Month | Rate 15 USD/Hr 4*160*15= 9600
 |  |  | Total - 58400 USD
Estimated Time - 4 Months
© 2018 Synectiks. All Rights Reserved. Proprietary and Confidential.