## Slide 1
Road Map
High Level Future State Road Map
Now
Current Initiatives
Product Design
Performance & Availability Management
Log Management
Alert Management
Workflow & Automation
Phase One
06-W4+07-W1+07-W2+07-W3
Performance / Availability Management
Cataloging with AWS Collectors
KPI from CloudWatch
Dashboards
Phase Two
07-W4+08-W1+08-W2
Activity Log
Alerting
Phase Three
08-W3+08-W4
RCA Central
ATP / Verification
Compliance Management
Alert Rules
Workflows
01
02
03
Documentation
Requirement & Use Cases
Architectures
RoadMap & Plans
Development
UI Screens
(Common + Alerts)
Few Customer Use Cases
Modules
Cataloging with AWS Collectors
Cloud watch Log
Cloud trail log
Flow Logs
Dashboards
Alert Rules
Search & Act
Dashboard Rules
Modules
Agent Activity logs
Insights
Activity Logs
Rule based inhibit /silence / dedup
Diagnostics
Discovery / Orchestration
Insights
Service Desk
Insights
Integrations
Modules
Explorer
Split Window Analysis
Implementation
Log Management
Alerting

## Slide 2
July W1
July W2
July W3
July W4
Aug W1
Aug W2
Aug W3
Aug W4
Design Sprints
Development Sprints
Phase 1
Implementation
PH1 Modules
Requirements Documentation
S0
Sprints
S1
S2
S3
S4
Future Phases
Activities
Implement PH1 Modules
Deployment
User Guide
Artifacts
PH1 Modules
User Guide
Implementation
Development Sprints
Implementation
PH2 Modules
Environment Setup
S5
S6
S7
S8
Phase 2
Activities
Complete Workflow, Ticketing spec
Artifacts
Requirement Spec
Docs
Activities
Implement PH1 Modules
Feed Back / Changes
User Guide
Artifacts
PH2 Modules
User Guide
Implementation
Activities
Implement PH3 Modules
Feed Back / Changes
User Guide
Artifacts
PH2 Modules
User Guide
Implementation
Activities
Test / Change
Artifacts
ATP results
Verification
Development Sprints
Production Movement Sprints
Proposed Project Timeline
Timeline

## Slide 3
Performed Activity
Task Name | Role | Effort
Requirement Gathering | Architect | 32 Hours
Architecture & RoadMap | Architect | 08 Hours
UX Design | UX Designer | 100 Hours
UI Development | UI Developer | 80 Hours
Activity