## Slide 1: High-level future state road map
Now
Admin
XXX Platform Maintenance
XXX Support
XXX Enhancements
XXX Cloud Migration
XXX Discovery
Consumer API
XXX
XXX
Admin
Vehicle content administration discovery
  Input and data requirements for XXX
  CMS product selection
  XXX content mapping
Consumer API
Foundation for future state Micro services architecture
Vehicle Content service using existing XXX content JSON
XXX service
XXX Service
Admin
Vehicle Content Administration
  Finalize CMS system
  Migrate marketing content to CMS
XXX Administration UI
Consumer API
XXX micro service from CMS
XXX event notification service
Rules event notification service
Aggregation service to use XXX content micro service
XXX future state discovery
Client Integration
Integrate with pilot consumer applications
Replace client java script API with Micro services
Admin
XXX Administration UI
Consumer API
XXX Micro service
  FY18-Q1
  FY17 Q4
FYQ2
Phase
1
Phase
2
Phase
3
Current
Initiatives

## Slide 2
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Design Sprints
Development Sprints
Phase 1
Implementation
XXX Content Service – Enriched Vehicle
Requirements Documentation
S0
Sprints
S1
S2
S3
S4
Activities
Procure AWS environment from D&IS
Review AWS Infrastructure and Technology Stack
Continuous Integration Build and Processes
Proposed Project Timeline
Future Phases
CHRISTMAS BREAK
Architecture
Architecture / Service Design
S5
S6
S7
S8
Activities
Define and Design services structure
Design caching strategy
Finalize AWS Technology Stack
AWS Initial Environment Setup
Implementation
Rules Service –
Enriched rules
Activities
National English Content service
Activities
Rules – Enriched rules service
Rules – Features Display
Development Sprints
Implementation
XXX Content Service
S9
S10
S11
S12
Implementation
Rules Service – Enriched rules
Activities
Rules – Enriched rules service
Rules – Conflicts resolution (Fix List)
Inventory Rules
Activities
XXX Content service
XXX Content service
S13
S14
Environment Setup
Sprint Cycle:
2 weeks design / development sprints
Deliverables:
By end of Phase 1
API Requirements
Design Document
Service API Document
Functional Test Cases
Performance Test Results
Deployment Guide
Source Code
Environment Refinement